## Setup
Key | Value | Notes
project | Riverside Logistics Hub — Phase 2 | Shown in the header
subtitle | Weekly progress · S-curve · Activity status | Optional
client | Northgate Developments | Optional
prepared_by | Project Controls
data_date | 2026-10-25 | YYYY-MM-DD or an Excel date
logo | RL | 1-3 letters for the badge

## Progress
Week | Planned % | Actual %
2026-07-05 | 1.5 | 1.2
2026-07-12 | 3.4 | 2.9
2026-07-19 | 5.8 | 5.1
2026-07-26 | 8.6 | 7.7
2026-08-02 | 11.9 | 10.4
2026-08-09 | 15.6 | 13.5
2026-08-16 | 19.7 | 17
2026-08-23 | 24.1 | 21
2026-08-30 | 28.8 | 25.4
2026-09-06 | 33.7 | 30.1
2026-09-13 | 38.8 | 35.2
2026-09-20 | 44 | 40.6
2026-09-27 | 49.2 | 46.1
2026-10-04 | 54.3 | 51.4
2026-10-11 | 59.2 | 56.3
2026-10-18 | 63.8 | 60.7
2026-10-25 | 68.1 | 64.2
2026-11-01 | 72
2026-11-08 | 75.6
2026-11-15 | 79
2026-11-22 | 82.2
2026-11-29 | 85.3
2026-12-06 | 88.3
2026-12-13 | 91.2
2026-12-20 | 94
2026-12-27 | 96.5
2027-01-03 | 98.5
2027-01-10 | 100

## Activities
Activity | Area | Weight % | Planned % | Actual %
Site clearance & grading | Zone A | 4 | 100 | 100
Piling | Zone A | 8 | 100 | 100
Pile caps & grade beams | Zone A | 6 | 100 | 96
Ground slab | Zone A | 7 | 92 | 85
Steel erection | Zone A | 12 | 78 | 71
Roof cladding | Zone A | 6 | 45 | 32
Piling | Zone B | 6 | 100 | 100
Pile caps & grade beams | Zone B | 5 | 88 | 80
Ground slab | Zone B | 6 | 70 | 58
Steel erection | Zone B | 10 | 40 | 22
Roof cladding | Zone B | 5 | 0 | 0
Underground drainage | External | 5 | 85 | 88
Road base & kerbs | External | 6 | 55 | 41
Asphalt | External | 4 | 0 | 0
HV substation civils | Utilities | 3 | 90 | 92
Fire water ring main | Utilities | 3 | 60 | 44
Office block fit-out | Office | 4 | 30 | 30

## Manpower
Week | Planned | Actual
2026-09-06 | 180 | 172
2026-09-13 | 190 | 181
2026-09-20 | 200 | 186
2026-09-27 | 210 | 195
2026-10-04 | 220 | 201
2026-10-11 | 230 | 204
2026-10-18 | 235 | 210
2026-10-25 | 240 | 206

## Concerns
Severity | Issue | Owner
High | Zone B steel erection 18% behind — second erection crew mobilises 3-Nov; recover 10% by end Nov. | Construction Mgr
High | Roof cladding sheets for Zone A delayed at supplier; revised delivery 5-Nov. Float exhausted. | Procurement
Medium | Road base held by late drainage testing in External zone; test witness booked 28-Oct. | QA/QC
Medium | Manpower 34 short of plan for 3 weeks running — welders and riggers. | HR / Subcontractor
Low | Fire water ring main trenching clashes with temporary laydown; relocation agreed. | Site Eng.

## ReadMe
How to use
1. Fill the sheets. Keep the header row names as they are.
2. Progress: one row per week, cumulative planned % and cumulative actual %. Leave Actual blank for future weeks.
3. Activities: weights should total 100. Planned and Actual are % complete per activity.
4. Manpower: average daily headcount per week.
5. Concerns: Severity is High / Medium / Low.
6. Save, then drag the file onto the dashboard. Nothing is uploaded anywhere.